## Agile Sprint Backlog
CS-2450 Sprint Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
Load Files | 3
Initial Implementation | 1 | Duncan | Complete | 1 | 1
Final Load Stuff | 2 | Carston | In-progress
Task
Task
Save Files | 3
Initial Implementation | 1 | Duncan | Complete | 1 | 1
Final Save Stuff | 2 | Andrew | Complete | 2 | 0 | 2
Task
Task
Documentation | 2
IED document | 2 | Aaron | In-progress | 2 | 0
Readme | 1 | Duncan | Complete | 1 | 0 | 1
Scrum master docs | 2 | Duncan | In-progress | 2 | 1 | 1
Task
User Story #4 | 0
Task
Task
Task
Task
User Story #5 | 0
Task
Task
Task
Task
TOTAL |  |  |  | 9 | 3 | 4 | 0 | 0 | 0 | 0 | 0